## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
Sprint 2 User Stories | Acceptance Criterion | Pass/Fail | Testing Details Initials; date; comments | Cross-Team Testing User Stories | Tester initials; date; comments (required if test failed) | Sprint 3 User Stories | Tester initials; date; comments (required if test failed)
AS A helper I WANT to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass |  | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I WANT to be able to access the needs page, SO THAT I can contribute to causes | Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass |  | Pass | SG - 11/7 | Fail
AS A helper, I WANT to be able to see when needs are not in the cupboard SO THAT I know what needs to be added | Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | JJ - Still working on cupboard implementation | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I WANT to be able to see what needs are in the cupboard SO THAT I know what is in stock | Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass |  | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I WANT to be able to add a need to my funding basket SO THAT I can contribute to needs | Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass |  | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I WANT to be able to login to the wbesite SO THAT I can make changes to my cart and fund causes | Given that I am not Logged in when I am on the website, then I need to be able to login to access the causes that I want to fund. | Pass |  | Pass | SG - 11/7 | Fail
AS A helper, I WANT to be able to search the website SO THAT I can find new causes to support | Given that I am logged in on the website when I am searching for causes, then I want to be able to search to find new causes. | Fail | JJ/NF - Navbar Box created, logic still being implemented for full functionality. | Pass | SG - 11/7 | Fail
AS A helper, I want to be able to fund different causes in my cart SO THAT I can checkout when I am finished browsing | Given that I am logged in when I am on the website, then I want to be able to put multiple items in my cart to fund. | Pass |  | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I want to be able to view causes that I have previously donated to SO THAT I may be able to donate to them again in the future. | Given that I have donated to causes previously when I have checked out, then I want to be able to view a history of these donations so that I may donate again in the future. | Fail | Functionality not currently implemented | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper I WANT to be able to interact with the website in a user friendly manner SO THAT I can access the backend easily. | Given that I am a helper when I am on the website, then I want to be able to interact with it in a user friendly manner. | Pass |  | Fail | SG - 11/7 Can get to the cupboard from home but not vice versa (have to traverse through user page) | Fail
AS A helper I WANT to be able to create an account SO THAT I can contribute to causes. | Given that I am a new user when I am on the website, then I want to be able to create an account so that I can contribute to causes. | Pass |  | Fail | SG - 11/7 Can go through account creation but account will not be stored | Fail
AS A helper, I WANT to be able to create new causes for others to support (Donation form) | Given that I am a helper on the website, I want to be able to create new causes for others to donate to. | Fail | Functionality not currently implemented | Fail | SG - 11/7 Talking to TA to connect front and back end | Fail
AS A helper, I WANT to be able to reset my password SO THAT I can still access the site in case I forget it. | Given that I forgot my password as a helper when I am on the website, then I want to be able to reset it to get back into the website. | Fail | JJ - Still working on implementation | Pass | SG - 11/7 Front end works, need to connect with backend | Fail
AS A helper, I WANT to be able to see a map view of who I am supporting SO THAT I can donate in person, etc. | Given that I am a helper when I am on the website, then I want to be able to see a map view of where the cause is located. | Fail | NF - Functionality to be implemented in Sprint 3 | Fail | SG - 11/7 10% enhancement to be implemented | Fail